## Timelines
Implementation of Internet phone
Task | 2017-02-22 |  | 2017-02-23 | 2017-02-24 | 2017-02-25 | 2017-02-26 | 2017-02-27 | 2017-02-28 | 2017-03-01 | 2017-03-02 | 2017-03-03 | 2017-03-04 | 2017-03-05 | 2017-03-06
1. Conceptualize
2. ready resources
3. Learn audio API
4. Test audio API
5. Attach mic API to socket
6. Test raw audio transmit
7. Add speaker API to socket
8. Test and complete in loopback
9. Test with other users
10. Write-up and paper work
11. Submit (laptop version)
12. Port to Raspi
Legends
delayed start
over deadline
on time progress
completed

## Project Status
Implementation of Internet phone
To Do List
To be completed by: |  |  | Deadline: |  | Highlight Activities
Chinmoy Mohapatra (MT2016505) |  |  | 2017-03-08 |  | No Highlight
Task # | Task | Start Date | End Date | Duration | % Done | Progress | Notes
1 | Conceptualize | 2017-02-22 | 2017-02-24 | 3 Day(s) | 100% | 100%
2 | ready resources | 2017-02-24 | 2017-02-24 | 1 Day(s) | 40% | 40% | learn and prepare github, add pulse audio, etc
3 | Learn audio API | 2017-02-24 | 2017-02-26 | 3 Day(s) | 0% | 0%
4 | Test audio API | 2017-02-24 | 2017-02-26 | 3 Day(s) | 0% | 0% | Start simultaneously with task # 3
5 | Attach mic API to socket | 2017-02-26 | 2017-02-27 | 2 Day(s) | 0% | 0% | Start after task # 4
6 | Test raw audio transmit | 2017-02-26 | 2017-02-27 | 2 Day(s) | 0% | 0% | Start simultaneously with task # 5
7 | Add speaker API to socket | 2017-02-27 | 2017-02-27 | 1 Day(s) | 0% | 0% | Start after task # 6
8 | Test and complete in loopback | 2017-02-28 | 2017-03-01 | 2 Day(s) | 0% | 0% | Start after task # 7
9 | Test with other users | 2017-03-03 | 2017-03-04 | 2 Day(s) | 0% | 0% | Start after task # 8
10 | Write-up and paper work | 2017-03-03 | 2017-03-05 | 3 Day(s) | 0% | 0% | Start simultaneously with task # 9
11 | Submit (laptop version) | 2017-03-05 | 2017-03-05 | 1 Day(s) | 0% | 0% | Start after task # 10
12 | Port to Raspi | 2017-03-03 | TBD | #VALUE! | 0% | 0% | Start simultaneously with task # 9

## Settings & Calculations (hidden)
Highlight Settings
The tables below store settings and calculations for the Highlight Activities drop down list. Any changes could result in errors or loss of functionality.
No Highlight |  |  | No Highlight
Interval: | Start: | End: | Due:
This Week | 2017-02-20 | 2017-02-26 | This Week [20 Feb - 26 Feb]
This Month | 2017-02-01 | 2017-02-28 | This Month [1 - 28, Feb]
This Quarter | 2017-01-01 | 2017-04-30 | This Quarter [1 Jan - 30 Apr]
This Year | 2017-01-01 | 2017-12-31 | This Year [2017]
Interval: |  |  | Interval:
Last Week | 2017-02-13 | 2017-02-19 | Last Week [13 Feb - 19 Feb]
Last Month | 2017-01-01 | 2017-01-31 | Last Month [1 - 31, Jan]
Last Quarter | 2016-10-01 | 2016-12-31 | Last Quarter [1 Oct - 31 Dec]
Last Year | 2016-01-01 | 2016-12-31 | Last Year
Selected Highlight: | 1 | No Highlight | FALSE
Highlight Start
Highlight End
Formulas:
End: = [Start:]+6
End: = EDATE([Start:],1)-1